## Cover Page
eMediCare (An Online Medical Management System)
Product Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | 1.Kashish Manglani(POD Lead) 2.Shekhar Deshpande 3.Aditaya Maharana 4.Narendran Ravichandran 5.Swastika Maji | Abhik Raha : Mentor Kavitha : Trainer
Role
Signature
Date
Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 |  |  |  | C3: Protected
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Product Backlog Instructions C3: Protected Controlled Copy
Backlog Worksheet
This sheet has to be filled while doing "Create Product Backlog" task in the Initial Envisioning Phase.
The Product backlog worksheet contains a list of features/requirements that the business would want to implement in an application. This worksheet would continue to exist from the beginning to the end of the project. The Product Owner maintains it by adding, modifying, removing any of the items listed there. They can also change the priority of the items so long as they are not being worked by the team in the ongoing Sprint. Most of the re-ordering would happen just before the Sprint Planning meeting. To ensure this kind of continuous update, this worksheet could be re-visited during periodic intervals once during the release elaboration Phase and thereafter during the project execution. The changes to the Product backlog could be triggered from several sources in terms of inclusion of new features / bugs/ known issues based on the stakeholder requests and the effort, schedule for the same would also be re-visited in the product backlog worksheet. Fill the following fields in the product backlog worksheet for each feature.
| User Story ID | <Provide unique ID for each User story>
| User Story Name | <Provide the theme/name of the User story or a high level requirement> Eg: User login Registration Mail notification
| User Story Role | < Provide who would be end User of the User story>. Details of who would use that functionality Eg:End User Admin Teacher Conference attendee
| User Story Details | <Provide description of what the User want> Provide details on "As a/an" particular user what the user wants. Eg: As a conference attendee, I want to be able to register online
| Acceptance criteria | <Specify the Acceptance criteria> Acceptance criteria define the boundaries of a user story, and are used to confirm when a story is completed and working as intended. So for the above example, the acceptance criteria could include: A user cannot submit a form without completing all the mandatory fields Information from the form is stored in the registrations database.
| Sprint | Sprint in which the user story is planned to completed. Select it from the drop down. Story Point is given in Fibonacci series of upto 21. For any User story if the estimation goes beyond 21, then the user story has to be broken down.
| Story point | A story point is a metric used in agile project management and development to determine (or estimate) the difficulty of implementing a given story. Select the story point that will be assigned to the user story from the drop down (in Fibonacci series) during the sprint planning meeting while estimating an user story.
| Done | Yes/No field, that can be selected from drop down based on an user is completed or not
| Added in Sprint | Provide sprint number when the particular User Story was handled
| Closed in sprint | Provide sprint number when the particular User Story was completed
| Actual Story Points | Actual story point burned for an user story while developing. Select from the drop down (in Fibonacci series)
Charts
| Sprint | This value is non-editable. Represents the Sprint numbers
| Story Points remaining | Enter the total story points calculated for the Sprint.
| Done | Enter the total story points that was "Done" in the sprint
| Variation | This value is non-editable. Variation is calculated as [(Current sprint's story point remaining + done) - (Previous sprint's story point remaining + done) + Previous sprint's variation]
| Percent Complete | Percentage completed is calculated as [(Done story point of the sprint/(Done story point + story point remaining)) *100]
| Release Burn Down Chart | 1. A typical release Burn Down chart would enable the Product Owner to assess as to how each iteration is progressing towards realizing the release goal. They would be able to assess the number of features that are going to make it (or) not make it to the release based on the number of features delivered by the team in each iteration. 2. Based on the progress being made by the team, the Product Owner may decide to add more Sprints within a release (if it is a feature driven release) or cut down some of the features from the Release backlog (if it is a Date driven release). The release burn down chart would be automatically plotted based on the data given on the Release burn down table with story points remaining and the done.

## Backlog
Product Backlog eMediCare Project ID: INTADM21AJ007 C3: Protected Controlled Copy
Done
User Story Id | User Story Name | User Story Role | User Story Details | Acceptance criteria | Sprint | Story Point | Done | Added in Sprint | Closed in sprint | Actual Story Points
1 | Admin Login | Admin | As an Admin I should be able to Login using my ID and Password | 1.AdminId and password is needed 2.Password must be at least 8 characters long 3. Password must be encrypted 4. if the admin is valid the home page will be displayed to him 5.An alert message should be displayed to admin if password is required. 6.Error popup should be displayed and prompts user to re-login if the password is incorrect. | 1
2 | Update admin's Profile | Admin | As an Admin I should be able to update my profile(Admin name, username, password | 1.AdminId and OTP is needed(Phone number and OTP must be in between 0-9 | 1
3 | Add Doctors | Admin | As an Admin I should be able to add Doctors | 1. Doctor's Id and password is alloted 2. doctors details added in database | 1
4 | Remove Doctors | Admin | As an Admin I should be able to Remove Doctors | 1.DoctorId and DoctorName is needed 2.Doctor's details will not be shown in patient's feed | 1
5 | View Doctor's Details | Admin | As an Admin I should be able to view Doctor's Details | 1.DoctorId and DoctorName is needed | 1
6 | View number of Patients | Admin | As an admin I should be able to view total number of users | 1.Table will be shown containing the patient's ID and Name, Address and Phone number | 1
7 | View Patient's Feedback | Admin | As an Admin I should be able to view Patient's Feedback or Complaints | 1.PatientId and PatientName is needed | 2
8 | Patient Login | Patient | As a patient I should be able to Login using my ID and password | 1.PatientId and password is needed 2.Password must be at least 8 characters long 3. Password should be encrypted 4. if the user is valid the home page will be displayed to him 5.An alert message should be displayed to user if password is required. 6.Error popup should be displayed and prompts user to re-login if the password is incorrect. | 1
9 | Update Patient's Profile | Patient | As a patient I should be able to update my profile(Patient Name, username, password, Phone number, age Height, weight, Address, sugar level, BP, colestrol) | 1.PatientId and OTP is needed(Phone number and OTP must be in between 0-9) | 1
10 | View Doctor's Details | Patient | As a patient I can see the doctor's name , doctor's Id and specialization | 1.DoctorId and DoctorName is needed 2.After successfull login of patient | 1
11 | Take online appointments | Patient | As a patient I should be able to book appointment | 1.DoctorId and DoctorName is needed | 1
12 | Take e-prescription | Patient | As a patient I can see my prescription shared by the doctor | 1.Prescription should be only in jpg, jpeg, doc, docx and pdf format | 2
13 | View Patient's reports(report sent by doctor after checkup) | Patient | As a patient I can see my reports which were sent by the doctor | 1.PatientReportID will require 2.After successful checkup 3.Cant be edited | 2
14 | Feedback | Patient | As a patient I should be able to give feedback | 1.DoctorId and DoctorName is needed | 2
15 | Cancel online appointments | Patient | As a patient I can cancel my upcoming online appointment of Doctor | 1.AppointmentID is required 2.Patient can only cancel their upcoming appoinments | 2
16 | View appointments | Patient | As a Patient I can view all my appointments | 1.Only if patient has taken any appointment earlier | 2
17 | Send Lab Report | Patient | As a Patient I can send my lab reports to doctor. | 1.DoctorId and AppointmentID is needed 2.After successful checkup (If needed) 3.File upload section is needed for uploading the lab report(only in jgp,jpeg,doc,docx, pdf) | 2
18 | Doctor Login | Doctor | As a doctor I should be able to Login using my ID and Password | 1.Doctorid and password is needed 2.Password must be at least 8 characters long 3. Password must be encrypted 4. if the admin is valid the home page will be displayed to him 5.An alert message should be displayed to admin if password is required. 6.Error popup should be displayed and prompts user to re-login if the password is incorrect. | 1
19 | Update Doctor's Profile | Doctor | As a Doctor I should be able to edit the details( Doctor's Name, username, password, Phone number, age Height, weight, Address, Specialization) | 1.DoctorId and OTP is needed(Phone number and OTP must be in between 0-9 | 1
20 | View appoinments | Doctor | As a doctor I should be able to view the appoinments | 1.Only if patient has book any appointment for a particular doctor | 2
21 | Show Patient Details | Doctor | As a doctor I should be able to view the details of the particular patient who booked appoinment |  | 2
22 | Give e-prescription | Doctor | As a doctor I should be able to give e-prescription to patient | 1.Only in jpg, jpeg, doc, docx and pdf format | 2
23 | View lab reports | Doctor | As a doctor I should be able to view the particular patients lab reports who booked the appoinment | 1.PatientId and PatientName is needed | 2
24 | Give final report to patient | Doctor | As a doctor I should be able to give final report after full check up of particular patient | 1.PatientID is needed 2.Only jpg, jpeg, doc, docx, pdf | 2

## Charts
Release Burndown
Only edit shaded columns, others are calculated
Sprint | Story points |  |  | Percent Complete | Min | Max
| Remaining | Done | Variation
1 | 100 | 75 | 0 | 43% | 0 | 100
2 | 170 | 150 | 145 | 47% | -145 | 25
3 | 190 | 120 | 135 | 39% | -135 | 55
Yes
No

## Sheet1 (hidden)
0
5
10
20
30
50
80
130
200
400
1000